## Guidelines
DEFECT AND DAMAGE REPAIR LIST
The reason for the "Defect Damage Repair List" is to have a proper tool to follow up all the deficiencies that are made by whomever; Ships staff / auditor / superintendent etc. Whatever remark / observation that are made have to be followed up in a proper way till the job is completed and the observation can be closed. It is the purpose that there is only one Deficiency and Observation Master-list on board that covers all the observations.This list should be stored in the common filing system.
The planned maintenance system on board covers all the planned maintenance and has a proper follow up in the system. During the daily routine inspections carried out by the ships staff a lot of unscheduled jobs will be identified that need to be recorded on a kind of a work-list which allow the ships staff to follow it up and distribute the work. The amended "Defect Damage Repair List" will be the new work-list besides the work-list that comes out of the PMS system
It is the purpose that these unscheduled jobs are reported in the "Defect Damage Repair List" by the ships staff with the observer code: “ST”
Reporting to office | At each end of the month an updated "Defect Damage Repair List" has to be e-mailed to the superintendent.
Item No. | This is a unique number for each item noted. In the present format, the no. of entries are limited to '30'. As the number goes above that, click the box "Enter Rows" to enter the no. of rows required
Date Recorded | Enter the date the deficiency was originally recorded
Type Of Defiency | The 'Type of Defiency' may be recorded as DEF = Deficiency ( Any deficiency or upgradation job recorded during an inspection whether by Ship staff, or Supdt or Third party Auditors NC = Non Conformity ( Refer External / Internal Audit Reports, Port State Control & Flag State observations ) OBS = Observations ( Ref External / Internal Audit Reports, Marine & Technical deficiencyor observations) CRI = Critical Equipment ( any critical equipment failure) COC = Condition of Class / Memo
Observer codes | Different observers codes have been created in order distinguish who made the observation. These remarks have to be reported with the code
ST = Ships staff
ST has to be used as explained above whenever ships staff finds an observation or a job that has to be carried out needs to be recorded in this form under the code “ST”.
SUP = Owner Superintendent / Marine Superintendent / Technical Superintendent
During the routine inspections by the superintendent he will also report his observations to the master previously under the form "Defect Damage Repair List".
The superintendent might fill out his remarks directly onboard in the Master-list, either he sends his remarks per e-mail to master and he has to insert them in the Master-list.
CL = Class Surveyor
During annual, intermediate or renewal survey class surveyors might give observations / remarks. All Conditions of Class / Imp Memos / Non conformities and observation recorded during an ISM / ISPS Audit should be recorded here
FSC = Flag State Control
During flag state inspections the inspector might have some observations / remarks.
PSC = Port State Control
During port state inspections the inspector might have some observations / remarks.Normally port state inspectors will give you also a date when the deficiency has to be completed. This completion date needs to be reported in the column Description of “Target date.”
TER = Terminal remarks
Nowadays terminals might also audit your vessel and make some remarks / observations.
OMT = SIRE / CDI
Oil Majors vetting & CDI inspection remarks
OTHER
A drop down list has been created in those cells from which you can choose the observer code.
Action Taken or Required | In this column you have to fill out a brief description what has to be done in order to solve the observation.
Target date | Enter the target date as set out by Ship Staff , Superintendent or as per Requirement (Port State control or COC etc)
PO Ref No. | Whenever spare parts are required to complete a job and the spare parts are ordered then the Purchase Order (PO) number has to be filled out in this column. It will give you an easy reference to trace back for which job a dedicated spare parts have been requested.
Status Codes | The purpose of the status code is to have a proper follow up of what the status is of the Deficiency / observation. Different codes have been created in order to distinguish the status. The codes have to be adapted along with the changes in the status. It is important that the correct abbreviation of the status code is used.
NS = Not Started
Whenever an observation is made it has to be entered with this code.
IP = In-progress
Whenever a job has started then the code has to be changed from “NS” to “IP”. Note that some jobs might take a long time before they are completed i.e. de-rusting and painting of a dedicated area on board. With this code everybody knows that the job has been started and is in progress.
WS = Waiting spare parts
For many jobs you might require spare parts before you actually can start the job. If this is the case then the code “WS” has to be used.
DD = Deferred to dry-dock.
Some deficiencies / observations cannot be solved on board and need to be carried out in dry-dock. These deficiencies have to be recorded with the code “DD”. This is also a good tool to continuously update the dry-dock list. It doesn’t mean that the dry-dock requisition has to be made immediately but it will remember us that we don’t forget the job when we are going to start the preparation for the dry-dock specification. Note that during the course of a certain period sometimes a job that was deferred to dry-dock can be solved on board, then this code has to be changed to the status: “CP”
CP = Completed
Whenever a job is completed the status code has to be changed to “CP”
Date completed | In this column you have to fill out the date when observation deficiency is repaired and can be reported as completed.
Work Sheets | Defect-Damage : Generally the jobs shall be listed here. (Jobs related to Dry Dock shall be listed in REFMAN software.)
Completed : Completed jobs from sheet "Defect-Damage" (with Status Code "CP") shall be listed here. (Jobs related to Dry Dock shall be listed in REFMAN software.)
Filtering Tool | The spreadsheet is set up as a database and has a simple filtering tool where you quickly can sort the observations according to your needs. I.e. if you want to sort the deficiencies on the status code then click on the arrow in the status code and choose ascending. It will sort the table alphabetically and you will find all the jobs that have the same code grouped. A selection can be made i.e. with the code “NS” and this selection can be printed and be used as a work-list with jobs that not yet have been started. You are also able to sort on a dedicated code and it will give you only these observations with the same code. If you want to have again the complete list then selects “all” and the complete list appears.
IMPORTANT NOTE
This form is used as a tool for onboard work-list and for reporting to GOODWOOD office ONLY.
THE DOCUMENT MIGHT NOT BE SHOWN TO A THIRD PARTY SUCH AS OIL MAJORS ETC.

## Defect-Damage
| Vessel: | ENERGY R |  |  | Date of Report: | 2019-11-14
Please refer to the sheet "Guidelines" before completing the below form. Jobs related to Dry Dock shall be listed in REFMAN software.
No. | Date Recorded | Type of Deficiency | Description of Deficiency | Observer code | Action Taken or Required | Target Date | PO Ref No. | Status Code | Date Completed | PRICE FOR SPARES/REPAIR
1 | 14/11/2019 | OBS | M.E.Exhaust bellow in the the exhaust trunking above the exhaust manifold | ST | bellow to be replaced with new bellow, new spare bellow to be supplied . |  |  | NS
2 | 14/11/2019 | OBS | oil leak observed from M.E. Shaft seal and oil collected in main engine pit | ST | to be attended during next docking. |  |  | NS
3 | 14/11/2019 | OBS | oil leak observed from fwd. stern tube seal. | ST | Seal to be renewed during next docking. |  |  | NS
4 | 14/11/2019 | OBS | HFO purifier water in oil sensor not in operation | ST | to check and order for sensor |  |  | NS
5 | 14/11/2019 | OBS | OWS 15 ppm monitor was instaled recently. No back up data for old is available on board. | ST | management to take call before take over |  |  | NS
6 | 14/11/2019 | OBS | IGS scrubber tower sight glass having soft patch | ST |  |  |  | NS
7 | 14/11/2019 | OBS | lagging near incinerator found oil soaked and damaged | ST |  |  |  | NS
8 | 14/11/2019 | OBS | boiler mountings lagging found damaged and missing | ST |  |  |  | NS
9 | 14/11/2019 | OBS | oil leak stains observed from all 3 A.E'S fly wheel . | ST | leaks to be rectified
10 | 14/11/2019 | OBS | no.1 A.E fuel filter leaking | ST | leaks to be rectified
11 | 14/11/2019 | OBS | Boiler water circ p/p sucting valve on boiler 2 leaking from the flange | ST | gasket to renew
12 | 14/11/2019 | OBS | boiler no2water controller gland leaking | ST | leaks to be rectified
13 | 14/11/2019 | OBS | M.E. JCW Preheater end cover gasket leaking | ST | gasket to renew
14 | 14/11/2019 | OBS | no.1 A.E. Fuel oi booster P/P Leaking from the top cover | ST | gasket to renew
15 | 14/11/2019 | OBS | M.E. Fuel oil heaters lagging missing | ST | laggings to be renewed
16 | 14/11/2019 | OBS | gas leak observed from sewage treatment plant | ST
17 | 14/11/2019 | OBS | Sewage treatment plant discharge efflunet is not tested on board. | ST
19 | 14/11/2019 | OBS | L.T. Cooler fresh water inlet pressure gauge defective. | ST
20 | 14/11/2019 | OBS | steam leakage obsereved from the C.O.P warming up valve drain line. | ST
21 | 14/11/2019 | OBS | M.E. under piston cover gaskets leaking | ST | gaskets to renew
22 | 14/11/2019 | OBS | M.E. cam case cover gaskets leaking | ST | gaskets to renew
23 | 14/11/2019 | OBS | no.2 bilge fire and general service p/p seal leaking | ST | seals to order and renew
24 | 14/11/2019 | OBS | OWS and sewage ovebd valve rusted | ST | to be derusted and painted
25 | 14/11/2019 | OBS | Main Air compressor lube oil pressure gauge defective. | ST | pressure guage to order to renew
26 | 14/11/2019 | OBS | no records for M.E. Peformance on NCR, (No performance reports on any load were provided) | ST
27 | 14/11/2019 | OBS | no records for A.E. Peformance on 85% Load, (No performance reports on any load were provided) | ST
28 | 14/11/2019 | OBS | Stby HFO purifier operation not witnessed | ST
29 | 14/11/2019 | OBS | M.E. Bearing clearances and crank shaft deflection reports were not provided | ST
30 | 14/11/2019 | OBS | Inventory of spares for both engine and deck machineries not provided | ST
31 | 14/11/2019 | OBS | M.E. spares studs are rusted | ST
32 | 14/11/2019 | OBS | inventory of stores for deck ,engine and cabin not provided | ST
33 | 14/11/2019 | OBS | M.E.Air cooler air side leaking from the gasket. | ST
34 | 14/11/2019 | OBS | AHU A/C no.2 Condenser is not having any gas | ST
35 | 14/11/2019 | OBS | Funnel Platform is too dirty and needs cleaning and painting. | ST | cleaning and paiting will be done after take over of the vessel.
36 | 14/11/2019 | OBS | FWG sea water outlet pipe corroded and having soft patch | ST | pipeline to be renewed
37 | 14/11/2019 | OBS | FWG Production was found to bearound 22 M.T. whereas the capacity is 35 M.T. | ST | to be cleaned and investigate
38 | 14/11/2019 | OBS | Running acommodation A/C was not effective | ST
39 | 14/11/2019 | OBS | various leakage observed in remote valve hydraulics around 200L | ST
40 | 14/11/2019 | OBS | Ballast tank gauges are highly erratic | ST | suspecting sensor line choked or damaged, same need to be renewed
41 | 14/11/2019 | OBS | Error observed in draft gauges, need to check when alongside | ST | suspecting sensor line choked or damaged, same need to be renewed
42 | 14/11/2019 | OBS | Ships performance monitoring system not operational, touch screen in CCR defective | ST | screen need to be renewed and calibrated with system
43 | 14/11/2019 | OBS | Various P.V. valves leaking on deck | ST | to be overhauled, if required seat to be renewed
44 | 14/11/2019 | OBS | P/V valve flame screen needs renewal | ST | to be renewed
45 | 14/11/2019 | OBS | Ballast tank vent cover found wasted | ST | need to be replaced
46 | 14/11/2019 | OBS | Ballast tank vent flame screen need to be renewed | ST | need to be renewed.
47 | 14/11/2019 | OBS | C.O.W. line fwd. pressure gauge faded | ST | need to be renewed.
48 | 14/11/2019 | OBS | Deck air line from acommodation to fwd found to be heavily rusted | ST | need to be renewed.
49 | 14/11/2019 | OBS | F.W. line from acommodation to fwd found to be heavily rusted | ST | need to be renewed.
50 | 14/11/2019 | OBS | V/V hydraulics line on deck found to be wasted badly in few sections | ST | need to be renewed.
51 | 14/11/2019 | OBS | cow branch lines need to be derusted at the bottom | ST | need to be derust and check for heavy pittings
52 | 14/11/2019 | OBS | U clamps for Valve hydraulics ,deck air and F.W line need to be renewed. | ST | need to be renewed.
53 | 14/11/2019 | OBS | 78 NOS of foam extinguisher gas catridges expiring on dec 2019 | ST | need to be replaced
54 | 14/11/2019 | OBS | SLOP (P) and (s) heating coils suspected to be leaking ,and most of the valves need to be replaced | ST | need to be replaced
55 | 14/11/2019 | OBS | Ballast sea chest valve found to be having difficulty in operation | ST | suspecting either the valve disc & shaft or seat ring damaged, causing restriction to valve in operation.
56 | 14/11/2019 | OBS | sacrificialflanges in E.R. sea water P/P' sfoundto be corroded and leak stains visible. | ST | need to be renewed.
57 | 14/11/2019 | OBS | Cargo lines pressure tested MAWP 10 bar ANNUALLY and 15 bar 2.5 yearly, whereas the design MAWP 15.9 and 2.5yrly test to be 23.8 bar. | ST | No records of testing to design pressure of 15.9 kgf/cm2, need to be tested to max
58 | 14/11/2019 | OBS | life boat self lowering wir drum found to be wated | ST | need to repaired
59 | 14/11/2019 | OBS | Aft ETA pick up rope found to be brittle and need to be replaced. | ST | need to be replaced
60 | 14/11/2019 | OBS | chocks and bollards found to be having deep grooving | ST | same need to be build up
61 | 14/11/2019 | OBS | Emgcy gen ,exhaust spark arrestor missing | ST | need to fabricate and fitt
62 | 14/11/2019 | OBS | Cargo valves operation timing were found to be slow for some of them | ST | need to be adjusted
63 | 14/11/2019 | OBS | No critical spare inventory provided | ST
64 | 14/11/2019 | OBS | ECDIS Screen having conitnous black dotted lines | ST | need to be renewed
65 | 14/11/2019 | OBS | various fittinngs on the crane found to be rusted and wasted badly | ST | need to be replaced
66 | 14/11/2019 | OBS | operating valve block on the crane found to be highly rusted. | ST | need derusting and renew if required
67 | 14/11/2019 | OBS | Office chairs found to be in bad condition | ST | need to be replaced
68 | 14/11/2019 | OBS | bridge window fixed washing line found to be having soft patch | ST | line need renewal
69 | 14/11/2019 | OBS | Aroud 40 tubelight shades have gone pale and found to be dull | ST | need to be renewed
70 | 14/11/2019 | OBS | AUTO PILOT system soft touch panel push button plastic coating damaged | ST | need to be renewed
71 | 14/11/2019 | OBS | ECR ACONIS PMS soft touch panel push buttons plastic coating damaged and button visible | ST | need to be renewed
72 | 14/11/2019 | OBS | AUTO PILOT system control setting unit cover damage | ST | need to be repaired
73 | 14/11/2019 | OBS | telegraph printer paper not winding | ST | need to be renewed
74 | 14/11/2019 | OBS | M.E. RPM repeater scale graduations faded on both the bridge wings | ST | need to be renewed
75 | 14/11/2019 | OBS | Rudder angle repeaters on the both the bridge wings foudto be faded | ST | need to be renewed
76 | 14/11/2019 | OBS | few of the acommodation drains and pipes are heavily corroded | ST | need to be renewed
77 | 14/11/2019 | OBS | out of 6 hot plates 2 nos of hot plates are defective | ST | need to be repaired
78 | 14/11/2019 | OBS | galley cooking oven not operational | ST | need to be repaired
79 | 14/11/2019 | OBS | Galley dish washer not operational | ST | need to be repaired
80 | 14/11/2019 | OBS | 3 nos of refregerators in galley are not operational | ST | need to be repaired
81 | 14/11/2019 | OBS | crew pantry dish washer not operational | ST | need to be repaired
82 | 14/11/2019 | OBS | Officers and crew mess room chairs have black stains | ST | needs to e renewed or shampoed
83 | 14/11/2019 | OBS | Mooring winches does not have permanent brake test marking | ST | need to test and marked permanently
84 | 14/11/2019 | OBS | mooring winches foundation, frames, fittings bolt heads found to be heavily rusted and wasted in most of the places | ST | need derusting and painting
85 | 14/11/2019 | OBS | Mooring winches brake stopper need to be renewed and adjusted. | ST | need to be renewed
86 | 14/11/2019 | OBS | deck plating from break of accomodation to manifold have heavy rust need to be derusted and painted | ST | need to be completely derusted and 3 coats of paints
87 | 14/11/2019 | OBS | Accomodation block and engine room casing has heavy rust stains need to be derusted and painted | ST | need derusting and painting
88 | 14/11/2019 | OBS | Deck pipelines and fitting have moderate rust | ST | needs derusting and paintng
89 | 14/11/2019 | OBS | FWD bosun store valve hyraulics solenoid valve blocks having leaks | ST | leaks need to be rectified, if required need to renew fittings/o rings
90 | 14/11/2019 | OBS | leaks observed from soleneoid valve blocks from the Remote valve hydraulic room | ST | leaks need to be rectified, if required need to renew fittings/o rings
91 | 14/11/2019 | OBS | As per present staff and there company instructions all portable gas equipments will be landed before handover. | ST | new meters need to be supplied
92 | 14/11/2019 | OBS | Presently vessel have 4 UTI and will be landing 2 UTI during handover | ST
93 | 14/11/2019 | OBS | Unitor Welding, refrigerant R404 and calibration gasses will be landing during handover | ST | new gases need to be supplied
94 | 14/11/2019 | OBS | Staff will be handing over 3 months photocopy of oil record books / Garbage and Ballast handling book. | ST
95 | 14/11/2019 | OBS | No cargo docs will be handed over and all be landed at China. Due to which we will not be able to create VEF or will not be able to produce any docs to cargo surveyor in load port for preparing VEF. | ST | need cargo docs for vef otherwise vessel has has to take 1.000 as VEF and protest from surveyor in load port
96 | 14/11/2019 | OBS | Vessel is fitted with NR20 /R149 type turbocharger and no spare T/C catridge is on board, need the same to be supplied NO.3 T/C is coming for MAJOR overhaul. | ST
97 | 14/11/2019 | OBS | Vessel is using Sigma paints, no OBM available onboard for ordering new paints. | ST | required OBM for further maintenance and to order correct paint
98 | 14/11/2019 | OBS | There is no BNWAS switch and alarm on bridge wings. | ST | need to be installed
99 | 14/11/2019 | OBS | Vessel does not have sewage holding tank and grey water holding tank for china as the discharge is prohibited in Dis.ports , modification of grey water discharge to bilge holding tank is in progress. | ST
100 | 14/11/2019 | OBS | Magnetic compass last deviation card prepared by shore technician was in 02 Dec 2017. | ST | required need deviation card
101 | 14/11/2019 | OBS | Officer and crew laundry 2 dryers not working | ST | need to br renewed
102 | 14/11/2019 | OBS | Fire flaps packing found brittle. | ST | need to be replaced
103 | 14/11/2019 | OBS | M.E. UNIT NO3,4 and 6 are over due for piston and cylinder head overhaul | ST
104 | 14/11/2019 | OBS | Engine room bulk heads ,pipelines and air ducts and exhaust trunking needs repainting as it is stained badly | ST
105 | 14/11/2019 | OBS | engine room air ducting found to be rusted badly and needs derusting, plate renewal and painting in various sections | ST
106 | 14/11/2019 | OBS | Upper deck common toilet flush switches defective | ST
107 | 14/11/2019 | OBS | A deck common toilet tap defective | ST
108 | 14/11/2019 | OBS | carpet flooring in officers smoke room, captain's cabin, c/e cabin were observed to be having black stains and partially damaged | ST | need to be replaced in next docking
109 | 14/11/2019 | OBS | Cabinet door hinges were found to be defective in various cabins | ST
110 | 14/11/2019 | OBS | M.E. 6 Nos of fuel valves were found to be leaking mildly | ST
111 | 14/11/2019 | OBS | 3 nos of M.E. Exhaust valve were found to be leaking from to cover | ST
112 | 14/11/2019 | OBS | 3 nos of fuel p/p shock absorbers of M.E. is having mild leakage | ST
113 | 14/11/2019 | OBS | Fire hydrant on deck and outside ECR found to be leaking | ST
114 | 14/11/2019 | OBS | conference room flooring found to be buckled and damaged | ST
115 | 14/11/2019 | OBS | No fire sensors installed in drying room | ST
116 | 14/11/2019 | OBS | 200 ltrs (100pcs) empty drum to be landed,as it restrict the access to funnel and vents for emergency generator room. | ST
117 | 14/11/2019 | OBS | Lots of garbage collected and same to be landed ashore, approx figures 10 cubic plastic, 3 cubic metal scrap, domestic wate. | ST
118 | 14/11/2019 | OBS | There is no arrangement or refregerator room for wet garbage collection | ST
119 | 14/11/2019 | OBS | Suez cabin all cabinet doors found damaged. | ST
120 | 14/11/2019 | OBS | Presently vessel have only 3 soft ropes, required 96mm x 250 meters soft rope in order to have 1 set forward and aft for tugs. | ST
121 | 14/11/2019 | OBS | No new spare rope tails available onboard, minimum 4 pcs required as spare for emergency | ST
122 | 14/11/2019 | OBS | Deck air line valve spindles heavily rusted and need renewal | ST
123 | 14/11/2019 | OBS | E/R Sludge aroud 25m3, bilge andgrey water mixture around 80 m3 to be landed. | ST
124 | 14/11/2019 | OBS | control airdrier operation not satisfactory | ST
125 | 14/11/2019 | OBS | E/R aft bilge well and stbd bilge well found to be having oily water mixture | ST
126 | 15/1/2019 | OBS | Elevator phone casing cracked and damaged | ST
127 | 15/11/2019 | OBS | Iridium antenna foundation cracked | ST
128 | 15/11/2019 | OBS | AM antenna securing bracket rusted and completely wasted | ST
129 | 15/11/2019 | OBS | P.A. System foundation on monkey island wasted | ST
130 | 15/11/2019 | OBS | NO presuure gauge fixed on the fire line in bridge wings | ST
131 | 15/11/2019 | OBS | No complete manuals sighted onboard | ST
132 | 15/11/2019 | OBS | Oily water separator operation not witnessed | ST
133 | 15/11/2019 | OBS | stby machinery Auto change over operation not witnessed | ST
134 | 15/11/2019 | OBS | Emergency generator AUTo stby start not witnessed | ST
135 | 15/11/2019 | OBS | M.E. UNIT NO. 3,4 and 6 exhaust valve are due for overhaul | ST
136 | 15/11/2019 | OBS | lube oil purifier bowl cleaning 2000 hr routine due | ST
137 | 15/11/2019 | OBS | Top up compressor major overhaul (4000 hr ) routine due | ST
138 | 15/11/2019 | OBS | AUX ENGINES bearing clearances and crank shaft deflection reports not provided | ST
139 | 15/11/2019 | OBS | LRIT certificate not available onboard | ST
140 | 16/11/2019 | OBS | COW line pressure gauge for pump room top not working in CCR | ST
141 | 16/11/2019 | OBS | COW line temperature gauges not working in CCR | ST
142 | 16/11/2019 | OBS | CCR telephone handset cord badly damage | ST
143 | 16/11/2019 | OBS | Steam chest pressure for No 2 COP gauge not working in CCR | ST
144 | 16/11/2019 | OBS | No 3 stbd Manifold valve or stbd manifold marpol line valves 323 & 311 leaking | ST
145 | 16/11/2019 | OBS | ALL 3 COPS PNEUMATIC DISCHARGE VALVES ARE LEAKING | ST
146 | 14/11/2019 | OBS | OBSERVERS ARE NOT PROVIDED WITH ANY SERVICE RECORD OF ANY LSA/FFA, BRIDGE, CCR & ER EQUIPMENTS OR ANY PERFORMANCE DOCUMENTS (I.E. PUMPING LOGS, VEF ETC) | ST | need to be replaced
CARGO SYSTEM, CRANES, WINCHES & WINDLASS WILL BE CHECKED DURING PRE ARRIVAL CHECK & DISCHARGING AT QINGDAO
[11 empty] | Type of Deficiency | Observer codes | Status Code
[11 empty] | DEF | ST | NS
[11 empty] | NC | SUP | IP
[11 empty] | OBS | CL | WS
[11 empty] | CRI | FSC | DD
[11 empty] | COC | PSC | CP
[11 empty] | OTHER | TER
OMT
2019-08-03
Insert Row

## Completed
Vessel: |  |  |  |  | Date of Report:
Please refer to the sheet "Guidelines" before completing the below form. Jobs related to Dry Dock shall be listed in REFMAN software.
No. | Date Recorded | Type of Deficiency | Description of Deficiency | Observer code | Action Taken or Required | Target Date | PO Ref No. | Status Code | Date Completed
1 | [5 empty] | 2019-11-30 |  | CP | 2019-09-02
2 | [5 empty] | 2019-11-30 |  | CP | 2019-09-02
3 | [5 empty] | 2019-11-30 |  | CP | 2019-09-03
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
[10 empty] | Type of Deficiency | Observer codes | Status Code
[10 empty] | DEF | ST | NS
[10 empty] | NC | SUP | IP
[10 empty] | OBS | CL | WS
[10 empty] | CRI | FSC | DD
[10 empty] | COC | PSC | CP
[10 empty] | OTHER | TER
OMT
Insert Row